## Sheet1
subcontactor name | Pundir Contractor
state name | Uttar Pradesh
district name | Shamli
block name | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | BOQ_Amount | Payment_Amount | TDS_Payment_Amount | Balance_ Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10%
52963
52963 | Badhpura VILLAGE- Pipe Line Work | 2022-11-02 | 1 | 521983 | 0 | 521983 | 93957 | 615940 | 5219.83 | 26099.15 | 26099.15 | 52198.3 | 93957 | 36104 | 376263 |  | 79059 | 376263 |  | -1056533 | 376263 | 05-11-2022 NEFT/AXISP00334807145/RIUP22/1186/PUNDIR CONTRACT 376263.00 | -188845
52963 | GST release note | 2022-11-08 | 1 | 93957 | [10 empty] | 93957 |  |  | 93957 |  |  | 93957 | 23-11-2022 NEFT/AXISP00339736216/RIUP22/1337/PUNDIR CONTRACT 93957.00
52963 | Badhpura VILLAGE- Pipe Line Work | 2022-11-28 | 2 | 436346 | 36028 | 400318 | 72057 | 472375 | 4003.18 | 20015.9 | 40031.8 | 40031.8 | 72057 | 107775 | 188460 |  |  | 188460 |  |  | 188460 | 09-12-2022 NEFT/AXISP00345325357/RIUP22/1468/PUNDIR CONTRACT 188460.00
52963 | Badhpura VILLAGE- Pipe Line Work | 2023-01-03 | 3 | 218625 | 0 | 218625 | 39353 | 257978 | 2186.25 | 10931.25 | 21862.5 | 21862.5 | 39353 | 56927 | 104855 |  |  | 104855 |  |  | 104855 | 06-01-2023 NEFT/AXISP00352522092/RIUP22/1798/PUNDIR CONTRACT 104855.00
52963 | GST release note | 2023-01-13 | 2 | 72057 | [10 empty] | 72057 |  |  | 72057 |  |  | 72057 | 18-01-2023 NEFT/AXISP00355697025/RIUP22/1868/PUNDIR CONTRACT ₹ 72,057.00
52963 | GST release note | 2023-04-29 | 3 | 39353 | [10 empty] | 39353 |  |  | 100000 | 1000 |  | 99000 | 23-01-2023 NEFT/AXISP00356620200/RIUP22/1939/PUNDIR CONTRACT ₹ 99,000.00
52963 | Badhpura VILLAGE- Pipe Line Work | 2023-07-07 | 4 | 52600 | 0 | 52600 | 9468 | 62068 | 526 | 2630 | 0 | 0 | 9468 | 0 | 49444 |  |  | 50000 | 500 |  | 49500 | 16-02-2023 NEFT/AXISP00363867491/RIUP22/2197/PUNDIR CONTRACT ₹ 49,500.00
52963 | GST release note | 2023-09-11 | 4 | 9468 |  | 9468 | 0 | 9468 | 0 | 0 | 0 | 0 | 0 | 0 | 9468 |  |  | 150000 | 1500 |  | 148500 | 25-08-2023 NEFT/AXISP00418295270/RIUP23/1701/PUNDIR CONTRACTOR 148500.00
52963 | Badhpura VILLAGE- Pipe Line Work | 2023-07-07 | 14 | 11675 | 0 | 11675 | 2102 | 13777 | 116.75 | 583.75 | 1167.5 | 1167.5 | 2102 | 2875 | 5764
52963 | GST release note |  | 14 | 2102 |  | 2102 | 0 | 2102 | 0 | 0 | 0 | 0 | 0 | 0 | 2102
52963 | Badhpura VILLAGE- Pipe Line Work | 2025-01-30 | 12 | 2200 | 0 | 2200 | 396 | 2596 | 22 | 110 | 220 | 220 | 396 | 0 | 1628
52963 | GST release note |  | 12 | 396 |  | 396 | 0 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 396
53871
53871 | Mohammadpur Rai VILLAGE- Pipe Line Work | 2023-01-05 | 4 | 671619 | 90070 | 581549 | 104679 | 686228 | 5815.49 | 29077.45 | 58154.9 | 58154.9 | 104679 | 53117 | 377230 |  | 79059 | 377230 |  |  | 377230 | 09-01-2023 NEFT/AXISP00353549285/RIUP22/1820/PUNDIR CONTRACTOR 377230.00 | -106584
53871 | GST release note | 2023-04-29 | 4 | 104679 | [10 empty] | 104679 |  |  | 300000 | 3000 |  | 297000 | 04-03-2023 NEFT/AXISP00368679029/RIUP22/2455/PUNDIR CONTRACT 297000.00
53871 | Mohammadpur Rai VILLAGE- Pipe Line Work | 2023-02-27 | 5 | 761724 | 72056 | 689668 | 124140 | 813808 | 6896.68 | 34483.4 | 68966.8 | 68966.8 | 124140 | 0 | 510355 |  |  | 150000 | 1500 |  | 148500 | 14-03-2023 NEFT/AXISP00371304697/RIUP22/2567/PUNDIR CONTRACT 148500.00
53871 | GST release note | 2023-04-29 | 5 | 124140 | [10 empty] | 124140 |  |  | 50000 | 500 |  | 49500 | 11-04-2023 NEFT/AXISP00380905283/SPUP23/0072/PUNDIR CONTRACT 49500.00
53871 | Mohammadpur Rai VILLAGE- Pipe Line Work | 2023-04-07 | 1 | 540146 | 0 | 540146 | 97226 | 637372 | 5401.46 | 27007.3 | 54014.6 | 54014.6 | 97226 | 78327 | 321381 |  |  | 300000 | 3000 |  | 297000 | 20-04-2023 20-04-2023 NEFT/AXISP00383281367/SPUP23/0213/PUNDIR CONTRACT 297000.00
53871 | GST release note | 2023-05-13 | 1 | 97226 | [10 empty] | 97226 |  |  | 228819 |  |  | 228819 | 02-05-2023 NEFT/AXISP00386671976/RIUP23/055/PUNDIR ₹ 2,28,819.00
53871 | Mohammadpur Rai VILLAGE- Pipe Line Work | 2023-08-01 | 7 | 11299 |  | 11299 | 2034 | 13333 | 112.99 | 564.95 | 1129.9 | 1129.9 | 2034 | 0 | 8361 |  |  | 39736 |  |  | 39736 | 02-05-2023 NEFT/AXISP00386671977/RIUP23/054/PUNDIR ₹ 39,736.00
53871 | Mohammadpur Rai VILLAGE- Pipe Line Work | 2023-08-01 | 6 | 52650 | 13561 | 39089 | 7036 | 46125 | 390.89 | 1954.45 | 0 | 0 | 7036 | 0 | 36744 |  |  | 97226 |  |  | 97226 | 18-05-2023 NEFT/AXISP00391091649/RIUP23/282/PUNDIR CONTRACTO 97226.00
53871 | GST release note | 2023-09-11 | 6 | 7036 | 0 | 7036 | 0 | 7036 | 0 | 0 | 0 | 0 | 0 | 0 | 7036 |  |  | 100000 | 1000 |  | 99000 | 24-07-2023 NEFT/AXISP00408776188/RIUP23/1186/PUNDIR CONTRACT 99000.00
53871 | GST release note | 2023-09-12 | 7 | 2034 | 0 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 |  |  | 9070 |  |  | 9070 | 16-09-2023 NEFT/AXISP00425496277/RIUP23/2041/PUNDIR CONTRACTOR/PUNB0166010 ₹ 9,070.00
53871 | Mohammadpur Rai VILLAGE- Pipe Line Work | 2024-08-22 | 5 | 39860 |  | 39860 | 7175 | 47035 | 398.6 | 1993 | 3986 | 3986 | 7175 | 39860 | -10364 |  |  | 50000 | 500 |  | 49500 | 20-08-2024 NEFT/AXISP00530112325/RIUP24/1511/PUNDIR CONTRACTOR/PUNB0166010 49500.00
53871 | GST release note | 2024-08-22 | 5 | 7175 | [10 empty] | 7175
53871
57473 | Khivari VILLAGE- Pipe Line Work | 2023-05-18 | 2 | 472655 | 90069 | 382586 | 68865 | 451451 | 3825.86 | 19129.3 | 38258.6 | 38258.6 | 68865 | 4177 | 278936 | 57473 | 79329 | 278936 |  |  | 278936 | 29-05-2023 NEFT/AXISP00393085066/RIUP23/423/PUNDIR CONTRACTO 278936.00 | 28490
57473 | Khivari VILLAGE- Pipe Line Work | 2023-06-04 | 3 | 118659.16 | 0 | 118659.16 | 21359 | 140018 | 1186.5916 | 5932.958 | 11865.916 | 11865.916 | 21359 | 7670 | 80137 |  |  | 80138 |  |  | 80138 | 19-06-2023 NEFT/AXISP00399545670/RIUP23/712/PUNDIR CONTRACTO 80138.00
57473 | GST release note | 2023-07-04 | 2 | 68866 |  | 68866 |  | 68866 | [6 empty] | 68866 |  |  | 68866 |  |  | 68866 | 15-07-2023 NEFT/AXISP00407218704/RIUP23/1079/PUNDIR CONTRACT 68866.00
57473 | Khivari VILLAGE- Pipe Line Work | 2023-08-01 | 9 | 89072 |  | 89072 | 16033 | 105105 | 890.72 | 4453.6 | 8907.2 | 8907.2 | 16033 | 8251 | 57662 |  |  | 57662 |  |  | 57662 | 10-08-2023 NEFT/AXISP00414696959/RIUP23/1431/PUNDIR CONTRACT 57662.00
57473 | GST release note | 2023-09-11 | 3 | 21359 |  | 21359 | 0 | 21359 | 0 | 0 | 0 | 0 | 0 | 0 | 21359 |  |  | 21359 |  |  | 21359 | 18-09-2023 NEFT/AXISP00425751836/RIUP23/2040/PUNDIR CONTRACTOR/PUNB0166010 21359.00
57473 | GST release note | 2023-10-11 | 9 | 16033 |  | 16033 | 0 | 16033 | 0 | 0 | 0 | 0 | 0 | 0 | 16033 |  |  | 16033 |  |  | 16033 | 17-10-2023 NEFT/AXISP00435127450/RIUP23/2688/PUNDIR CONTRACTOR/PUNB0166010 16033.00
57473 | Khivari VILLAGE- Pipe Line Work | 2024-04-18 | 1 | 38947 | 36028 | 2919 | 525 | 3444 | 29.19 | 145.95 | 291.9 | 291.9 | 525 | 0 | 2160
57473 | GST release note |  | 1 | 525 |  | 525 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 525
57473 | Khivari VILLAGE- Pipe Line Work | 2024-05-30 | 2 | 28050 | 0 | 28050 | 5049 | 33099 | 280.5 | 1402.5 | 2805 | 2805 | 5049 | 0 | 20757
57473 | GST release note |  | 2 | 5049 |  | 5049 | 0 | 5049 | 0 | 0 | 0 | 0 | 0 | 0 | 5049
58072 | Asadpur Bamnauli VILLAGE- Pipe Line Work | 2023-08-01 | 8 | 455354 | 90070 | 365284 | 65751 | 431035 | 3652.84 | 18264.2 | 36528.4 | 36528.4 | 65751 | 5291 | 265019 | 58072 | 79832 | 150000 | 1500 |  | 148500 | 26-06-2023 NEFT/AXISP00400451245/RIUP23/887/PUNDIR CONTRACTOR 148500.00 | -152170
58072 | Asadpur Bamnauli VILLAGE- Pipe Line Work | 2023-09-02 | 10 | 182672 | 0 | 182672 | 32881 | 215553 | 1826.72 | 9133.6 | 18267.2 | 18267.2 | 32881 |  | 135177 |  |  | 100000 | 1000 |  | 99000 | 19-07-2023 NEFT/AXISP00407912722/RIUP23/1141/PUNDIR CONTRACT ₹ 99,000.00
58072 | GST Release note |  | 8 | 65751 |  | 65751 |  | 65751 | [6 empty] | 65751 |  |  | 17519 |  |  | 17519 | 14-08-2023 NEFT/AXISP00415473410/RIUP23/1491/PUNDIR CONTRACT 17519.00
58072 | GST Release note | 2023-10-11 | 10 | 32881 |  | 32881 |  | 32881 | [6 empty] | 32881 |  |  | 79200 |  |  | 79200 | 14-08-2023 NEFT/AXISP00415763061/RIUP23/1524/PUNDIR CONTRACT ₹ 79,200.00
58072 | Asadpur Bamnauli VILLAGE- Pipe Line Work | 2023-11-01 | 12 | 454349 | 3603 | 450746 | 81134 | 531880 | 4507.46 | 22537.3 | 45074.6 | 45074.6 | 81134 | 435 | 333117 |  |  | 50000 |  |  | 49500 | 11-09-2023 NEFT/AXISP00423685738/RIUP23/1957/PUNDIR CONTRACTOR/PUNB0166010 49500.00
58072 | GST Release note |  | 12 | 81134 |  | 81134 |  | 81134 | [6 empty] | 81134 |  |  | 6477 |  |  | 6477 | 13-09-2023 NEFT/AXISP00424687444/RIUP23/1999/PUNDIR CONTRACTOR/PUNB0166010 6477.00
58072 | Asadpur Bamnauli VILLAGE- Pipe Line Work | 2024-02-26 | 19 | 52230 | 0 | 52230 | 9401 | 61631 | 522.3 | 2611.5 | 5223 | 5223 | 9401 | 0 | 38650 |  |  | 65751 |  |  | 65751 | 16-09-2023 NEFT/AXISP00425496276/RIUP23/2042/PUNDIR CONTRACTOR/PUNB0166010 ₹ 65,751.00
58072 | GST Release note |  | 19 | 9401 | [10 empty] | 9401 |  |  | 32881 |  |  | 32881 | 17-10-2023 NEFT/AXISP00435127449/RIUP23/2687/PUNDIR CONTRACTOR/PUNB0166010 32881.00
58072 | Asadpur Bamnauli VILLAGE- Pipe Line Work | 2025-03-19 | 17 | 18700 | 0 | 18700 | 3366 | 22066 | 187 | 935 | 1870 | 1870 | 3366 | 0 | 13838 |  |  | 200000 | 2000 |  | 198000 | 09-11-2023 NEFT/AXISP00442541954/RIUP23/3182/PUNDIR CONTRACTOR/PUNB0166010 198000.00
58072 | Asadpur Bamnauli Debit Note | 2025-04-02 | 178 | 175000 | [10 empty] | 175000 |  |  | 135530 |  |  | 135530 | 29-11-2023 NEFT/AXISP00447355235/RIUP23/3481/PUNDIR CONTRACTOR/PUNB0166010 135530.00
58072 | [17 empty] | 81129 |  |  | 81129 | 18-12-2023 NEFT/AXISP00453898724/RIUP23/3809/PUNDIR CONTRACTOR/PUNB0166010 81129.00
58072 | [17 empty] | 38651 |  |  | 38651 | 24-04-2024 NEFT/AXISP00493457028/RIUP24/0255/PUNDIR CONTRACTOR/PUNB0166010 38651.00
58072
59171
59171 | Bamnoli Kairana VILLAGE- Pipe Line Work | 2023-10-09 | 11 | 308075 | 36028 | 272047 | 48968 | 321015 | 2720.47 | 13602.35 | 27204.7 | 27204.7 | 48968 | 128546 | 72768 |  | 81244 | 99000 |  |  | 99000 | 11-09-2023 NEFT/AXISP00423685739/RIUP23/1958/PUNDIR CONTRACTOR/PUNB0166010 99000.00 | -168251
59171 | Bamnoli Kairana VILLAGE- Pipe Line Work | 2023-12-27 | 15 | 122650 | 28194 | 94456 | 17002 | 111458 | 944.56 | 4722.8 | 9445.6 | 9445.6 | 17002 | 61853 | 8044 |  |  | 99000 |  |  | 99000 | 25-10-2023 NEFT/AXISP00436731131/RIUP23/2859/PUNDIR CONTRACTOR/PUNB0166010 99000.00
59171 | GST RELEASE NOTE |  | 11 | 48968 |  | 48968 | 0 | 48968 | 0 | 0 | 0 | 0 | 0 |  | 48968 |  |  | 48968 |  |  | 48968 | 18-11-2023 NEFT/AXISP00445057526/RIUP23/3300/PUNDIR CONTRACTOR/PUNB0166010 48968.00
59171 | GST RELEASE NOTE |  | 15 | 17002 |  | 17002 | 0 | 17002 | 0 | 0 | 0 | 0 | 0 |  | 17002 |  |  | 49500 |  |  | 49500 | 15-01-2024 NEFT/AXISP00462583112/RIUP23/4269/PUNDIR CONTRACTOR/PUNB0166010 49500.00
59171 | Bamnoli Kairana VILLAGE- Pipe Line Work | 2024-02-26 | 18 | 19548 | 0 | 19548 | 3519 | 23067 | 195.48 | 977.4 | 1954.8 | 1954.8 | 3519 | 19548 | -5082 |  |  | 17002 |  |  | 17002 | 18-01-2024 NEFT/AXISP00463439411/RIUP23/4327/PUNDIR CONTRACTOR/PUNB0166010 17002.00
59171 | GST RELEASE NOTE |  | 18 | 3519 | [10 empty] | 3519
60929
60929 | BARALA KUKARHERI VILLAGE PIPE LINE WOR | 2023-12-30 | 16 | 411113 | 90070 | 321043 | 57788 | 378831 | 3210.43 | 16052.15 | 32104.3 | 32104.3 | 57788 | 50073 | 187498 |  | 81248 | 1500000 | 15000 |  | 148500 | 18-12-2023 NEFT/AXISP00453885480/RIUP23/3838/PUNDIR CONTRACTOR/PUNB0166010 148500.00 | -167746
60929 | GST RELEASE NOTE |  | 16 | 57788 |  | 57788 | 0 | 57788 | 0 | 0 | 0 | 0 | 0 |  | 57788 |  |  | 39001 |  |  | 39001 | 10-01-2024 NEFT/AXISP00461151268/RIUP23/4142/PUNDIR CONTRACTOR/PUNB0166010 39001.00
60929 | BARALA KUKARHERI VILLAGE PIPE LINE WOR | 2023-12-30 | 17 | 187804 | 36028 | 151776 | 27320 | 179096 | 1517.76 | 7588.8 | 15177.6 | 15177.6 | 27320 | 7934 | 104380 |  |  | 104379 | 1043.79 |  | 104379 | 01-02-2024 NEFT/AXISP00467277206/RIUP23/4375/PUNDIR CONTRACTOR/PUNB0166010 104379.00
60929 | GST RELEASE NOTE |  | 16 | 27320 |  | 27320 | 0 | 27320 | 0 | 0 | 0 | 0 | 0 |  | 27320 |  |  | 27320 |  |  | 27320 | 26-02-2024 NEFT/AXISP00473983981/RIUP23/4693/PUNDIR CONTRACTOR/PUNB0166010 27320.00
60929 | BARALA KUKARHERI VILLAGE PIPE LINE WOR | 2024-03-31 | 20 | 633565 | 2.6 | 633562.4 | 114041 | 747603 | 6335.624 | 31678.12 | 63356.24 | 63356.24 | 114041 | 33807 | 435028 |  |  | 57788 |  |  | 57788 | 26-02-2024 NEFT/AXISP00473983982/RIUP23/4694/PUNDIR CONTRACTOR/PUNB0166010 57788.00
60929 | GST RELEASE NOTE |  | 20 | 114041 | [10 empty] | 114041 |  |  | 250000 | 2500 |  | 247500 | 28-05-2024 NEFT/AXISP00503313836/RIUP24/0633/PUNDIR CONTRACTOR/PUNB0166010 247500.00
60929 | BARALA KUKARHERI VILLAGE PIPE LINE WOR | 2024-07-28 | 3 | 354650 | 35228 | 319422 | 57496 | 376918 | 3194.22 | 15971.1 | 31942.2 | 31942.2 | 57496 | 137810 | 98562 |  |  | 300000 | 3000 |  | 297000 | 18-07-2024 NEFT/AXISP00519773559/RIUP24/1174/PUNDIR CONTRACTOR/PUNB0166010 297000.00
60929 | GST RELEASE NOTE |  | 3 | 57496 | [10 empty] | 57496 |  |  | 200000 | 2000 |  | 198000 | 03-08-2024 NEFT/AXISP00524511284/RIUP24/1354/PUNDIR CONTRACTOR/PUNB0166010 198000.00
60929 | BARALA KUKARHERI VILLAGE PIPE LINE WOR | 2024-10-26 | 8 | 279016.5 | 17615.5 | 261401 | 47052 | 308453 | 2614.01 | 13070.05 | 26140.1 | 26140.1 | 47052 | 4760 | 188676 |  |  | 80000 | 800 |  | 79200 | 20-08-2024 NEFT/AXISP00530112324/RIUP24/1509/PUNDIR CONTRACTOR/PUNB0166010 79200.00
60929 | GST RELEASE NOTE |  | 8 | 47052 | [10 empty] | 47052 |  |  | 120000 | 1200 |  | 118800 | 21-10-2024 NEFT/AXISP00556268915/RIUP24/2254/PUNDIR CONTRACTOR/PUNB0166010 118800.00
60929 | BARALA KUKARHERI VILLAGE PIPE LINE WOR | 2025-02-21 | 14 | 193914 | 0 | 193914 | 34905 | 228819 | 1939.14 | 9695.7 | 19391.4 | 19391.4 | 34905 | 0 | 143496 |  |  | 150000 | 1500 |  | 148500 | 14-11-2024 NEFT/AXISP00569818239/RIUP24/2483/PUNDIR CONTRACTOR/PUNB0166010 148500.00
60929 | GST RELEASE NOTE |  | 14 | 34905 | [10 empty] | 34905 |  |  | 200000 | 2000 |  | 198000 | 06-03-2025 NEFT/AXISP00629048192/RIUP24/3357/PUNDIR CONTRACTOR/PUNB0166010 198000.00
65505
65505 | JIJAULA ALIPURA Village - Pipeline work | 2024-08-14 | 4 | 313251 | 48439 | 264812 | 47666 | 312478 | 2648.12 | 13240.6 | 26481.2 | 26481.2 | 47666 | 23279 | 172681 |  | 81248 | 170000 | 1700 |  | 168300 | 21-08-2024 NEFT/AXISP00530350670/RIUP24/1510/PUNDIR CONTRACTOR/PUNB0166010 168300.00 | -245072
65505 | GST release note |  | 4 | 47666 | [10 empty] | 47666 |  |  | 100000 | 1000 |  | 99000 | 10-09-2024 NEFT/AXISP00538525504/RIUP24/1734/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65505 | JIJAULA ALIPURA Village - Pipeline work | 2024-09-16 | 6 | 202811.5 | 70456 | 132355.5 | 23824 | 156180 | 1323.555 | 6617.775 | 13235.55 | 13235.55 | 23824 | 15083.5 | 82860 |  |  | 150000 | 1500 |  | 148500 | 30-10-2024 NEFT/AXISP00561389908/RIUP24/2367/PUNDIR CONTRACTOR/PUNB0166010 148500.00
65505 | GST release note |  | 6 | 23824 | [10 empty] | 23824 |  |  | 150000 | 1500 |  | 148500 | 07-01-2025 NEFT/AXISP00595145647/RIUP24/2861/PUNDIR CONTRACTOR/PUNB0166010 148500.00
65505 | JIJAULA ALIPURA Village - Pipeline work | 2024-10-28 | 9 | 485910.1 | 2.1 | 485908 | 87463 | 573371 | 4859.08 | 24295.4 | 48590.8 | 48590.8 | 87463 | 31847.1 | 327724 |  |  | 200000 | 2000 |  | 200000 | 20-01-2025 NEFT/AXISP00600730125/RIUP24/2974/PUNDIR CONTRACTOR/PUNB0166010 200000.00
65505 | GST release note |  | 9 | 87463 | [10 empty] | 87463 |  |  | 100000 | 1000 |  | 99000 | 30-01-2025 NEFT/AXISP00606020254/RIUP24/3060/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65505 | JIJAULA ALIPURA Village - Pipeline work | 2024-12-26 | 11 | 302754 | 35228 | 267526 | 48155 | 315681 | 2675.26 | 13376.3 | 26752.6 | 26752.6 | 48155 | 173222 | 24747 |  |  | 100000 | 1000 |  | 99000 | 14-02-2025 NEFT/AXISP00616404528/RIUP24/3171/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65505 | GST release note |  | 11 | 48155 | [10 empty] | 48155 |  |  | 50000 | 500 |  | 49500 | 13-03-2025 NEFT/AXISP00633031176/RIUP24/3421/PUNDIR CONTRACTOR/PUNB0166010 49500.00
65505 | JIJAULA ALIPURA Village - Pipeline work | 2025-03-11 | 16 | 104500 | 0 | 104500 | 18810 | 123310 | 1045 | 5225 | 10450 | 10450 | 18810 | 0 | 77330 |  |  | 100000 | 1000 |  | 99000 | 28-03-2025 NEFT/AXISP00641450828/RIUP24/3509/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65505 | JIJAULA ALIPURA Village - Pipeline work | 2025-03-25 | 18 | 407846 | 0 | 407846 | 73412 | 481258 | 4078.46 | 20392.3 | 40784.6 | 40784.6 | 73412 | 0 | 301806 |  |  | 100000 | 1000 |  | 99000 | 09-04-2025 NEFT/AXISP00648889485/RIUP25/0065/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65505 | GST release note |  | 16 & 18 | 92222 | [10 empty] | 92222 |  |  | 1500000 | 15000 |  | 148500 | 02-05-2025 NEFT/AXISP00660145762/RIUP25/0190/PUNDIR CONTRACTOR/PUNB0166010 148500.00
65505 | [17 empty] | 170000 | 1700 |  | 173250 | 08-05-2025 NEFT/AXISP00663252909/RIUP25/0224/PUNDIR CONTRACTOR/PUNB0166010 173250.00
65505 | [17 empty] | 200000 | 2000 |  | 198000 | 05-06-2025 NEFT/AXISP00675041578/RIUP25/0419/PUNDIR CONTRACTOR/PUNB0166010 198000.00
65505 | [17 empty] | 100000 | 1000 |  | 99000 | 09-07-2025 NEFT/AXISP00688754315/RIUP25/0606/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65505
65606
65606 | Alipur Village kairana - Pipeline work | 2024-09-30 | 7 | 398656 | 17614 | 381042 | 68588 | 449630 | 3810.42 | 19052.1 | 38104.2 | 38104.2 | 68588 | 157533 | 124438 |  | 81248 | 100000 | 1000 |  | 99000 | 29-08-2024 NEFT/AXISP00533195027/RIUP24/1579/PUNDIR CONTRACTOR/PUNB0166010 99000.00 | -242767
65606 | GST release note |  | 7 | 68588 | [10 empty] | 68588 |  |  | 50000 | 500 |  | 49500 | 18-09-2024 NEFT/AXISP00541733391/RIUP24/1835/PUNDIR CONTRACTOR/PUNB0166010 49500.00
65606 | Alipur Village kairana - Pipeline work | 2024-11-20 | 10 | 246456 | 0 | 246456 | 44362 | 290818 | 2464.56 | 12322.8 | 24645.6 | 24645.6 | 44362 | 6085 | 176292 |  |  | 100000 | 1000 |  | 99000 | 26-09-2024 NEFT/AXISP00544686595/RIUP24/1935/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65606 | GST release note |  | 10 | 44362 | [10 empty] | 44362 |  |  | 1500000 | 15000 |  | 148500 | 05-10-2024 NEFT/AXISP00549438830/RIUP24/2128/PUNDIR CONTRACTOR/PUNB0166010 148500.00
65606 | Alipur Village kairana - Pipeline work | 2025-01-30 | 13 | 62307 | 0 | 62307 | 11215 | 73522 | 623.07 | 3115.35 | 6230.7 | 6230.7 | 11215 | 41009 | 5098 |  |  | 100000 | 1000 |  | 99000 | 28-11-2024 NEFT/AXISP00575911964/RIUP24/2571/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65606 | GST release note |  | 13 | 11215 | [10 empty] | 11215 |  |  | 100000 | 1000 |  | 99000 | 04-12-2024 NEFT/AXISP00579764038/RIUP24/2626/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65606 | Alipur Village kairana - Pipeline work | 2025-02-10 | 15 | 22000 | 0 | 22000 | 3960 | 25960 | 220 | 1100 | 2200 | 2200 | 3960 | 0 | 16280 |  |  | 100000 | 1000 |  | 99000 | 13-12-2024 NEFT/AXISP00583928107/RIUP24/2692/PUNDIR CONTRACTOR/PUNB0166010 99000.00
65606 | GST release note |  | 15 | 3960 | [10 empty] | 3960 |  |  | 100000 | 1000 |  |  | 11-07-2025 NEFT/AXISP00689824267/RIUP25/0655/PUNDIR CONTRACTOR/PUNB0166010 99000.00
67941
67941 | Dabheri Khurd village kairana - Pipeline work | 2025-02-08 | 14 A | 248955 | 35252 | 213703 | 38467 | 252170 | 2137.03 | 10685.15 | 21370.3 | 21370.3 | 38467 | 189560 | -31419 |  | 81248 | 100000 | 1000 |  | 99000 | 14-02-2025 NEFT/AXISP00616404529/RIUP24/3172/PUNDIR CONTRACTOR/PUNB0166010 99000.00 | -331725
67941 | Dabheri Khurd village kairana - Pipeline work | 2025-02-24 | 15 B | 67742 | 0 | 67742 | 12194 | 79936 | 677.42 | 3387.1 | 6774.2 | 6774.2 | 12194 | 29846 | 20283 |  |  | 100000 | 1000 |  | 99000 | 06-03-2025 NEFT/AXISP00629048191/RIUP24/3356/PUNDIR CONTRACTOR/PUNB0166010 99000.00
67941 | GST release note |  | 14 & 15 | 50661 | [10 empty] | 50661 |  |  | 100000 | 1000 |  | 99000 | 13-03-2025 NEFT/AXISP00633031177/RIUP24/3420/PUNDIR CONTRACTOR/PUNB0166010 99000.00
67941 | [17 empty] | 74250 | 742.5 |  | 74250 | 09-04-2025 NEFT/AXISP00648889484/RIUP25/0064/PUNDIR CONTRACTOR/PUNB0166010 74250.00
67941 | [17 empty] | 50000 | 500 |  | 49500 | 23-05-2025 NEFT/AXISP00669293555/RIUP25/0324/PUNDIR CONTRACTOR/PUNB0166010 49500.00
67941
67941
69278
69278 | madalapur Village Thana Bhawan Pipeline work | 2025-04-28 | 1 | 389594 |  | 389594 | 70127 | 459721 | 3895.94 | 19479.7 | 38959.4 | 38959.4 | 70127 | 5686.34 | 282613 |  |  | 200000 | 2000 |  | 198000 | 15-05-2025 NEFT/AXISP00666023349/RIUP25/0253/PUNDIR CONTRACTOR/PUNB0166010 198000.00 | -280016
69278 | madalapur Village Thana Bhawan Pipeline work | 2025-05-14 | 2 | 135229 |  | 135229 | 24341 | 159570 | 1352.29 | 6761.45 | 13522.9 | 13522.9 | 24341 | 45 | 100024 |  |  | 50000 |  |  | 50000 | 23-05-2025 NEFT/AXISP00669293556/RIUP25/0325/PUNDIR CONTRACTOR/PUNB0166010 50000.00
69278 | GST Release Note |  | 1 | 70127 | [10 empty] | 70127 |  |  | 300000 | 3000 |  | 297000 | 05-06-2025 NEFT/AXISP00675041576/RIUP25/0418/PUNDIR CONTRACTOR/PUNB0166010 297000.00
69278 | GST Release Note |  | 2 | 24341 | [10 empty] | 24341 |  |  | 150000 | 1500 |  | 148500 | 23-06-2025 NEFT/AXISP00681739129/RIUP25/0534/PUNDIR CONTRACTOR/PUNB0166010 148500.00
69278 | madalapur Village Thana Bhawan Pipeline work | 2025-02-26 | 4 | 239250 | 175000 | 64250 | 11565 | 75815 | 642.5 | 3212.5 | 6425 | 6425 | 11565 | 45 | 47500 |  |  | 150000 | 1500 |  | 148500 | 19-07-2025 NEFT/AXISP00692182490/RIUP25/0717/PUNDIR CONTRACTOR/PUNB0166010 148500.00
69278 | madalapur Village Thana Bhawan Pipeline work | 2025-07-11 | 6 | 68200 | 17626 | 50574 | 9103 | 59677 | 505.74 | 2528.7 | 5057.4 | 5057.4 | 9103 | 45 | 37379
69278 | GST Release Note |  | 4
69278 | GST Release Note |  | 6
70525
70525 | Mawi NON Ahatmal Village kairana - Pipeline work | 2025-07-12 | 7 | 55683 | 52878 | 2805 | 505 | 3310 | 28.05 | 140.25 | 280.5 | 280.5 | 505 |  | 2075 | [7 empty] | 2075
70525 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70525 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70525 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70525
70229
70229 | Bibipur Haitya Village kairana - Pipeline work | 2025-06-30 | 5 | 164352.46 | 17626 | 146726.46 | 26411 | 173137 | 1467.2646 | 7336.323 | 14672.646 | 14672.646 | 26411 | 65941 | 42636 | [7 empty] | 42636
70229 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70229 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70229 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70229
70229
70228
70228 | mamaur Village kairana - Pipeline work |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 82013 | [5 empty] | 0
70228 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70228 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70228 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70228
70228
70194
70194 | kaserwa Khrud village kairana - Pipeline work | 2025-05-29 | 3 | 680527.28 | 1.28 | 680526 | 122495 | 803021 | 6805.26 | 34026.3 | 68052.6 | 68052.6 | 122495 |  | 503589 |  |  | 200000 | 2000 |  | 198000 | 15-05-2025 NEFT/AXISP00666023349/RIUP25/0253/PUNDIR CONTRACTOR/PUNB0166010 198000.00 | -215916
70194 | GST Release Note |  | 3 | 122495 | [10 empty] | 122495 |  |  | 50000 |  |  | 50000 | 23-05-2025 NEFT/AXISP00669293556/RIUP25/0325/PUNDIR CONTRACTOR/PUNB0166010 50000.00
70194 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 300000 | 3000 |  | 297000 | 05-06-2025 NEFT/AXISP00675041576/RIUP25/0418/PUNDIR CONTRACTOR/PUNB0166010 297000.00
70194 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 150000 | 1500 |  | 148500 | 23-06-2025 NEFT/AXISP00681739129/RIUP25/0534/PUNDIR CONTRACTOR/PUNB0166010 148500.00
70194 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 150000 | 1500 |  | 148500 | 19-07-2025 NEFT/AXISP00692182490/RIUP25/0717/PUNDIR CONTRACTOR/PUNB0166010 148500.00
70194 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
70194
[8 empty] | 13671454 |  | 559650.076 | 1084032.102 | 1110131.252 | 2014741 | 1584366.94 | 8881672 | [5 empty] | 10904063 |  | -2025891
[12 empty] | Total Payable Amount Rs. - | [8 empty] | -2022391
Pundir Contractor
2025-05-23
[9 empty] | Total Bill Amount with GST |  | 13671454
[9 empty] | balance payable |  | -2022391
[9 empty] | Total Paid amount |  | 10904063
[9 empty] | Hold Amount |  | 2753813.43
[9 empty] | DPR Excess Hold |  | 1584366.94
[9 empty] | Advance / Surplus |  | -2022391
[9 empty] | GST Remaining |  | 302817